## Summary
Production Plan Report — Summary
KEY METRICS
Total Containers | On Time | Delayed | Delay % | Total Late Days | Capacity Issues | Gap Issues | Outsourcing Issues
39 | 13 | 26 | 66.7% | 277 | 0 | 564 | 0
EMPLOYEE OVERVIEW
Real Employees | Sim Employees | Total Plan Min | Assigned Min | Unassigned Min | Coverage % | Underutilized | Overloaded
56 | 0 | 1031474.4 | 1031474.4 | 0 | 100.0% | 3 | 1
CAPACITY SCENARIOS (Accumulated Employee Stats)
Scenario | Shift Hours | Includes Saturday | Working Days | Real Employees | Real Capacity Min | Shortage Min | Extra Employees (Global) | Coverage %

## Plan Workcenters
Production Plan — Workcenter Requirements
WC Code | WC Name | Total OTN (min) | Plan Days | Avg OTN/Day | Notes
w04 | Mag Welding Center | 236807.4 | 56 | 4228.7
w05 | Tig Welding Center | 158049.7 | 47 | 3362.8
m01 | Cnc Milling Center | 140756.2 | 82 | 1716.5
d03 | Manual Grinding Station | 118828.9 | 59 | 2014
p01 | Automated Packing Station | 64454.1 | 60 | 1074.2
pa01 | Assembly | 49741 | 54 | 921.1
l01 | Laser Cutting | 47946.1 | 53 | 904.6
m03 | Cnc Lathe Center | 44449.8 | 56 | 793.7
n01 | Electropolishing Center | 33337.8 | 40 | 833.4
b01 | Plate Bending | 25487.9 | 48 | 531
m05 | Drilling | 15804.6 | 39 | 405.2
w06 | Laser Welding | 13199 | 23 | 573.9
m06 | Drilling And Tapping | 13177.2 | 42 | 313.7
u01 | Heavy Punching Center | 9995.7 | 29 | 344.7
m02 | Nc Milling Center | 9177.6 | 21 | 437
d05 | Helper Work General | 9010.3 | 12 | 750.9
s02 | Disc Sawing Center | 7249.8 | 28 | 258.9
l02 | Pipe Laser | 6386 | 25 | 255.4
s01 | Band Sawing | 5682.4 | 33 | 172.2
b04 | Plate Rolling | 5132.3 | 24 | 213.8
b02 | Pipe Bending | 4891.2 | 13 | 376.2
w03 | Stud Welding | 3137.4 | 16 | 196.1
c01 | Wire Cutting | 2742.2 | 6 | 457
t01 | Trowalizing Center | 2558.9 | 31 | 82.5
l03 | Engraving | 1529 | 14 | 109.2
y01 | Laser Rust Removal | 1436 | 13 | 110.5
q02 | Checking | 295.8 | 11 | 26.9
r01 | Riveting Center | 180 | 2 | 90
q01 | Quality Testing Center | 30 | 1 | 30

## Equipment Capacity
Equipment Capacity vs Plan Requirements
WC Code | WC Name | Stations | Total OTN (min) | Plan Days | Days Needed 8h | Recover 8h | Days Needed 10h | Recover 10h | Days Needed 12h | Recover 12h
w04 | Mag Welding Center | 37 | 236807.4 | 56 | 13.3 | -42.7 | 10.7 | -45.3 | 8.9 | -47.1
w05 | Tig Welding Center | 15 | 158049.7 | 47 | 22 | -25 | 17.6 | -29.4 | 14.6 | -32.4
m01 | Cnc Milling Center | 4 | 140756.2 | 82 | 73.3 | -8.7 | 58.6 | -23.4 | 48.9 | -33.1
d03 | Manual Grinding Station | 31 | 118828.9 | 59 | 8 | -51 | 6.4 | -52.6 | 5.3 | -53.7
p01 | Automated Packing Station | 16 | 64454.1 | 60 | 8.4 | -51.6 | 6.7 | -53.3 | 5.6 | -54.4
pa01 | Assembly | 4 | 49741 | 54 | 25.9 | -28.1 | 20.7 | -33.3 | 17.3 | -36.7
l01 | Laser Cutting | 4 | 47946.1 | 53 | 25 | -28 | 20 | -33 | 16.6 | -36.4
m03 | Cnc Lathe Center | 2 | 44449.8 | 56 | 46.3 | -9.7 | 37 | -19 | 30.9 | -25.1
n01 | Electropolishing Center | 2 | 33337.8 | 40 | 34.7 | -5.3 | 27.8 | -12.2 | 23.2 | -16.8
b01 | Plate Bending | 3 | 25487.9 | 48 | 17.7 | -30.3 | 14.2 | -33.8 | 11.8 | -36.2
m05 | Drilling | 8 | 15804.6 | 39 | 4.1 | -34.9 | 3.3 | -35.7 | 2.7 | -36.3
w06 | Laser Welding | 2 | 13199 | 23 | 13.7 | -9.3 | 11 | -12 | 9.2 | -13.8
m06 | Drilling And Tapping | 3 | 13177.2 | 42 | 9.2 | -32.8 | 7.3 | -34.7 | 6.1 | -35.9
u01 | Heavy Punching Center | 4 | 9995.7 | 29 | 5.2 | -23.8 | 4.2 | -24.8 | 3.5 | -25.5
m02 | Nc Milling Center | 6 | 9177.6 | 21 | 3.2 | -17.8 | 2.5 | -18.5 | 2.1 | -18.9
d05 | Helper Work General | 1 | 9010.3 | 12 | 18.8 | 6.8 | 15 | 3 | 12.5 | 0.5
s02 | Disc Sawing Center | 3 | 7249.8 | 28 | 5 | -23 | 4 | -24 | 3.4 | -24.6
l02 | Pipe Laser | 1 | 6386 | 25 | 13.3 | -11.7 | 10.6 | -14.4 | 8.9 | -16.1
s01 | Band Sawing | 3 | 5682.4 | 33 | 3.9 | -29.1 | 3.2 | -29.8 | 2.6 | -30.4
b04 | Plate Rolling | 1 | 5132.3 | 24 | 10.7 | -13.3 | 8.6 | -15.4 | 7.1 | -16.9
b02 | Pipe Bending | 2 | 4891.2 | 13 | 5.1 | -7.9 | 4.1 | -8.9 | 3.4 | -9.6
w03 | Stud Welding | 1 | 3137.4 | 16 | 6.5 | -9.5 | 5.2 | -10.8 | 4.4 | -11.6
c01 | Wire Cutting | 3 | 2742.2 | 6 | 1.9 | -4.1 | 1.5 | -4.5 | 1.3 | -4.7
t01 | Trowalizing Center | 1 | 2558.9 | 31 | 5.3 | -25.7 | 4.3 | -26.7 | 3.6 | -27.4
l03 | Engraving | 1 | 1529 | 14 | 3.2 | -10.8 | 2.5 | -11.5 | 2.1 | -11.9
y01 | Laser Rust Removal | 1 | 1436 | 13 | 3 | -10 | 2.4 | -10.6 | 2 | -11
q02 | Checking | 1 | 295.8 | 11 | 0.6 | -10.4 | 0.5 | -10.5 | 0.4 | -10.6
r01 | Riveting Center | 3 | 180 | 2 | 0.1 | -1.9 | 0.1 | -1.9 | 0.1 | -1.9
q01 | Quality Testing Center | 7 | 30 | 1 | 0 | -1 | 0 | -1 | 0 | -1

## Employee Capacity
Employee Capacity vs Plan Requirements
WC Code | WC Name | Total OTN (min) | Plan Days | P1 Count | P1 Cap 8h (min) | P1 Days 8h | P1 Days 10h | P1 Days 12h | All Count | All Cap 8h (min) | All Days 8h | All Days 10h | All Days 12h | Priority-1 Employees | All Skilled Employees
w04 | Mag Welding Center | 236807.4 | 56 | 17 | 8160 | 29 | 23.2 | 19.3 | 24 | 11520 | 20.6 | 16.4 | 13.7 | Chang Zhiju, Chen Yuwen, Gong Qingsuo, Huang Hao, Ji Zhongwei, Li Zhipeng, Liu Jiankai, Ma Jishan, Shao Changjun, Song Zhilong, Wang Ruifei, Wang Xushun, Wang Yongxi, Wu Lianjun, Xia Hongxian, Yin Xianfa, Zhang Chongliang | Cao Cheng, Chang Zhiju, Chen Yuwen, Gong Qingsuo, Huang Hao, JI Yipin, Ji Zhongwei, Li Zhipeng, Liu Jiankai, Ma Jishan, Shao Changjun, Song Zhilong, Sui Sixian, Sun Guofeng, Wang Ruifei, Wang Xuelin, Wang Xushun, Wang Yongxi, Wu Lianjun, Xia Hongxian, Yin Xianfa, Yin Yanqiu, Zhang Chongliang, Zhao Wei
w05 | Tig Welding Center | 158049.7 | 47 | 5 | 2400 | 65.9 | 52.7 | 43.9 | 19 | 9120 | 17.3 | 13.9 | 11.6 | JI Yipin, Sun Guofeng, Wang Xuelin, Yin Yanqiu, Zhao Wei | Cao Cheng, Chang Zhiju, Chen Yuwen, Gong Qingsuo, JI Yipin, Ji Zhongwei, Ma Jishan, Song Zhilong, Sun Guofeng, Wang Ruifei, Wang Xuelin, Wang Xushun, Wang Yongxi, Wu Lianjun, Xia Hongxian, Yin Xianfa, Yin Yanqiu, Zhang Chongliang, Zhao Wei
m01 | Cnc Milling Center | 140756.2 | 82 | 2 | 960 | 146.6 | 117.3 | 97.7 | 5 | 2400 | 58.6 | 46.9 | 39.1 | Gavin Liu, Mei Shijun | Gavin Liu, Guo Guangsheng, Jiang Xiugang, Mei Shijun, Zhao Baojun
d03 | Manual Grinding Station | 118828.9 | 59 | 2 | 960 | 123.8 | 99 | 82.5 | 7 | 3360 | 35.4 | 28.3 | 23.6 | Gong Qingguo, Shang Hechang | Gong Qingguo, JI Yipin, Jiang Quannian, Luo Jun, Shang Hechang, Wang Ye, Zhang Liyuan
p01 | Automated Packing Station | 64454.1 | 60 | 0 | 0 | N/A | N/A | N/A | 8 | 3840 | 16.8 | 13.4 | 11.2 |  | Diao Xiaowei, Li Lefeng, Shang Hechang, Wang Cunxiang, Yang Xiaoxiang, Zhang Baohua, Zhang Weizhao, Zhang Zhen
pa01 | Assembly | 49741 | 54 | 3 | 1440 | 34.5 | 27.6 | 23 | 11 | 5280 | 9.4 | 7.5 | 6.3 | Wang Cunxiang, Yang Xiaoxiang, Zhang Zhen | Diao Xiaowei, Li Lefeng, Liu Xu, Luo Jun, Shang Hechang, Wang Cunxiang, Xu Qinye, Yang Xiaoxiang, Zhang Baohua, Zhang Weizhao, Zhang Zhen
l01 | Laser Cutting | 47946.1 | 53 | 2 | 960 | 49.9 | 40 | 33.3 | 3 | 1440 | 33.3 | 26.6 | 22.2 | Tang Jixiao, Wang Jian | Cai Zhihua, Tang Jixiao, Wang Jian
m03 | Cnc Lathe Center | 44449.8 | 56 | 3 | 1440 | 30.9 | 24.7 | 20.6 | 6 | 2880 | 15.4 | 12.3 | 10.3 | Guo Guangsheng, Wang Xiaochen, Yu Wei | Gao Quanhe, Gavin Liu, Guo Guangsheng, Mei Shijun, Wang Xiaochen, Yu Wei
n01 | Electropolishing Center | 33337.8 | 40 | 0 | 0 | N/A | N/A | N/A | 3 | 1440 | 23.2 | 18.5 | 15.4 |  | Li Lefeng, Liu Xu, Xu Qinye
b01 | Plate Bending | 25487.9 | 48 | 2 | 960 | 26.5 | 21.2 | 17.7 | 6 | 2880 | 8.8 | 7.1 | 5.9 | Bing Zhaochun, Cai Zhihua | Bing Zhaochun, Cai Zhihua, Huang Zelun, Jiang Xiugang, Sun Kewen, Wang Jian
m05 | Drilling | 15804.6 | 39 | 0 | 0 | N/A | N/A | N/A | 4 | 1920 | 8.2 | 6.6 | 5.5 |  | Gao Quanhe, Jiang Xiugang, Mei Shijun, Yu Wei
w06 | Laser Welding | 13199 | 23 | 0 | 0 | N/A | N/A | N/A | 10 | 4800 | 2.7 | 2.2 | 1.8 |  | Chen Yuwen, Sui Sixian, Sun Guofeng, Wang Ruifei, Wang Xuelin, Wu Lianjun, Xia Hongxian, Yin Xianfa, Yin Yanqiu, Zhang Chongliang
m06 | Drilling And Tapping | 13177.2 | 42 | 0 | 0 | N/A | N/A | N/A | 3 | 1440 | 9.2 | 7.3 | 6.1 |  | Wang Cunxiang, Yu Wei, Zhao Ruifei
u01 | Heavy Punching Center | 9995.7 | 29 | 1 | 480 | 20.8 | 16.7 | 13.9 | 2 | 960 | 10.4 | 8.3 | 6.9 | Sun Kewen | Sun Gongxu, Sun Kewen
m02 | Nc Milling Center | 9177.6 | 21 | 1 | 480 | 19.1 | 15.3 | 12.7 | 4 | 1920 | 4.8 | 3.8 | 3.2 | Jiang Xiugang | Gao Quanhe, Gavin Liu, Jiang Xiugang, Mei Shijun
d05 | Helper Work General | 9010.3 | 12 | 5 | 2400 | 3.8 | 3 | 2.5 | 11 | 5280 | 1.7 | 1.4 | 1.1 | Diao Xiaowei, Li Lefeng, Liu Xu, Xu Qinye, Zhang Weizhao | Diao Xiaowei, Li Lefeng, Liu Xu, Shang Hechang, Sun Gongxu, Wang Cunxiang, Xu Qinye, Yang Xiaoxiang, Zhang Liyuan, Zhang Weizhao, Zhang Zhen
s02 | Disc Sawing Center | 7249.8 | 28 | 0 | 0 | N/A | N/A | N/A | 1 | 480 | 15.1 | 12.1 | 10.1 |  | Sun Gongxu
l02 | Pipe Laser | 6386 | 25 | 1 | 480 | 13.3 | 10.6 | 8.9 | 4 | 1920 | 3.3 | 2.7 | 2.2 | Huang Zelun | Cai Zhihua, Huang Zelun, Sun Kewen, Wang Jian
s01 | Band Sawing | 5682.4 | 33 | 1 | 480 | 11.8 | 9.5 | 7.9 | 3 | 1440 | 3.9 | 3.2 | 2.6 | Sun Gongxu | Sun Gongxu, Sun Kewen, Yu Wei
b04 | Plate Rolling | 5132.3 | 24 | 0 | 0 | N/A | N/A | N/A | 4 | 1920 | 2.7 | 2.1 | 1.8 |  | Huang Zelun, Wang Jian, Wu Lianjun, Zhang Baohua
b02 | Pipe Bending | 4891.2 | 13 | 0 | 0 | N/A | N/A | N/A | 5 | 2400 | 2 | 1.6 | 1.4 |  | Cai Zhihua, Gao Quanhe, Huang Zelun, Sun Kewen, Wang Jian
w03 | Stud Welding | 3137.4 | 16 | 0 | 0 | N/A | N/A | N/A | 5 | 2400 | 1.3 | 1 | 0.9 |  | Chen Yuwen, Song Zhilong, Xia Hongxian, Yin Xianfa, Zhang Chongliang
c01 | Wire Cutting | 2742.2 | 6 | 1 | 480 | 5.7 | 4.6 | 3.8 | 3 | 1440 | 1.9 | 1.5 | 1.3 | Zhang Baohua | Cai Zhihua, Gavin Liu, Zhang Baohua
t01 | Trowalizing Center | 2558.9 | 31 | 0 | 0 | N/A | N/A | N/A | 3 | 1440 | 1.8 | 1.4 | 1.2 |  | Gong Qingguo, JI Yipin, Luo Jun
l03 | Engraving | 1529 | 14 | 0 | 0 | N/A | N/A | N/A | 4 | 1920 | 0.8 | 0.6 | 0.5 |  | Cai Zhihua, Diao Xiaowei, Yin Yanqiu, Zhang Chongliang
y01 | Laser Rust Removal | 1436 | 13 | 0 | 0 | N/A | N/A | N/A | 2 | 960 | 1.5 | 1.2 | 1 |  | Wu Lianjun, Zhang Zhen
q02 | Checking | 295.8 | 11 | 0 | 0 | N/A | N/A | N/A | 8 | 3840 | 0.1 | 0.1 | 0.1 |  | Diao Xiaowei, Li Lefeng, Shang Hechang, Wang Cunxiang, Yang Xiaoxiang, Zhang Baohua, Zhang Weizhao, Zhang Zhen
r01 | Riveting Center | 180 | 2 | 0 | 0 | N/A | N/A | N/A | 4 | 1920 | 0.1 | 0.1 | 0.1 |  | Diao Xiaowei, Wang Xushun, Xu Qinye, Zhang Weizhao
q01 | Quality Testing Center | 30 | 1 | 0 | 0 | N/A | N/A | N/A | 8 | 3840 | 0 | 0 | 0 |  | Diao Xiaowei, Li Lefeng, Shang Hechang, Wang Cunxiang, Yang Xiaoxiang, Zhang Baohua, Zhang Weizhao, Zhang Zhen

## Bottleneck Actions
Bottleneck Workcenter Action Plans
Rank | Workcenter | Severity | Action Start | Action End | Span Days | Current Cap (min) | Avg Daily Usage | Utilization % | BN Utilization % | Gap Days | Gap Count | Recommended Shift | Workers Needed | Extra Machines | Affected Containers | Recommendation
1 | Heavy Punching Center (u01) | LOW | 2026-04-14 | 2026-05-01 | 17 | 960 | 344.7 | 35.9% | 0.0% | 10 | 3 | 8h | 1 | 0 | 2 | Reallocate partial capacity (~5.0% increase needed) to cover 10 gap-days. Focus on 'u01 → d03' transition (10 days lost, 2 occurrences).
2 | Laser Welding (w06) | LOW | 2026-04-13 | 2026-06-12 | 60 | 4800 | 573.9 | 12.0% | 0.0% | 0 | 0 | 8h | 0 | 0 | 3
3 | Helper Work General (d05) | LOW | 2026-04-13 | 2026-06-12 | 60 | 5280 | 750.9 | 14.2% | 0.0% | 0 | 0 | 8h | 0 | 0 | 3
4 | Automated Packing Station (p01) | MEDIUM | 2026-04-16 | 2026-06-17 | 62 | 3840 | 1074.2 | 28.0% | 0.0% | 44 | 6 | 8h | 1 | 0 | 24 | Reallocate partial capacity (~5.5% increase needed) to cover 44 gap-days. Focus on 'p01 → m01' transition (64 days lost, 4 occurrences).
5 | Mag Welding Center (w04) | MEDIUM | 2026-04-13 | 2026-05-26 | 43 | 11520 | 4228.7 | 36.7% | 0.0% | 25 | 5 | 8h | 1 | 0 | 8 | Reallocate partial capacity (~1.0% increase needed) to cover 25 gap-days. Focus on 'w04 → d03' transition (140 days lost, 27 occurrences).
6 | Manual Grinding Station (d03) | CRITICAL | 2026-04-17 | 2026-05-19 | 32 | 3360 | 2014 | 59.9% | 0.0% | 525 | 95 | 16h | 3 | 2 | 18 | Add 5.2 worker(s) to cover 525 gap-days. Focus on 'd03 → m01' transition (633 days lost, 50 occurrences). Consider adding a second shift or machine.
7 | Assembly (pa01) | LOW | 2026-05-08 | 2026-05-24 | 16 | 5280 | 921.1 | 17.4% | 0.0% | 7 | 2 | 8h | 1 | 0 | 10 | Reallocate partial capacity (~0.6% increase needed) to cover 7 gap-days. Focus on 'pa01 → m01' transition (52 days lost, 3 occurrences).
8 | Cnc Milling Center (m01) | CRITICAL | 2026-05-15 | 2026-07-14 | 60 | 2400 | 1716.5 | 71.5% | 0.0% | 1454 | 131 | 20h | 6 | 5 | 18 | Add 14.5 worker(s) to cover 1454 gap-days. Focus on 'd03 → m01' transition (633 days lost, 50 occurrences). Consider adding a second shift or machine.
9 | Disc Sawing Center (s02) | LOW | 2026-04-13 | 2026-05-02 | 19 | 480 | 258.9 | 53.9% | 0.0% | 11 | 2 | 8h | 1 | 0 | 1 | Reallocate partial capacity (~11.0% increase needed) to cover 11 gap-days. Focus on 's02 → m01' transition (30 days lost, 3 occurrences).
10 | Cnc Lathe Center (m03) | CRITICAL | 2026-04-23 | 2026-06-04 | 42 | 2880 | 793.8 | 27.6% | 0.0% | 430 | 51 | 18h | 2 | 1 | 9 | Add 4.3 worker(s) to cover 430 gap-days. Focus on 'm03 → m01' transition (232 days lost, 33 occurrences). Consider adding a second shift or machine.
11 | Drilling And Tapping (m06) | LOW | 2026-05-23 | 2026-06-08 | 16 | 1440 | 313.7 | 21.8% | 0.0% | 4 | 1 | 8h | 1 | 0 | 10 | Reallocate partial capacity (~1.3% increase needed) to cover 4 gap-days. Focus on 'm03 → m06' transition (4 days lost, 1 occurrences).
12 | Tig Welding Center (w05) | MEDIUM | 2026-04-13 | 2026-05-23 | 40 | 9120 | 3362.8 | 36.9% | 0.0% | 37 | 4 | 8h | 1 | 0 | 8 | Reallocate partial capacity (~1.9% increase needed) to cover 37 gap-days. Focus on 'w05 → w05' transition (151 days lost, 25 occurrences).
13 | Quality Testing Center (q01) | LOW | 2026-04-13 | 2026-06-12 | 60 | 3840 | 30 | 0.8% | 0.0% | 0 | 0 | 8h | 0 | 0 | 1
14 | Electropolishing Center (n01) | CRITICAL | 2026-04-26 | 2026-06-01 | 36 | 1440 | 833.5 | 57.9% | 0.0% | 159 | 30 | 16h | 1 | 0 | 10 | Add 1.6 worker(s) to cover 159 gap-days. Focus on 'w05 → n01' transition (137 days lost, 24 occurrences). Consider adding a second shift or machine.
15 | Plate Bending (b01) | MEDIUM | 2026-04-16 | 2026-05-19 | 33 | 2880 | 531 | 18.4% | 0.0% | 29 | 4 | 8h | 1 | 0 | 5 | Reallocate partial capacity (~4.8% increase needed) to cover 29 gap-days. Focus on 'l01 → b01' transition (25 days lost, 3 occurrences).
16 | Drilling (m05) | LOW | 2026-04-13 | 2026-06-12 | 60 | 1920 | 405.2 | 21.1% | 0.0% | 0 | 0 | 8h | 0 | 0 | 4
17 | Checking (q02) | LOW | 2026-04-13 | 2026-06-12 | 60 | 3840 | 26.9 | 0.7% | 0.0% | 0 | 0 | 8h | 0 | 0 | 3
18 | Trowalizing Center (t01) | LOW | 2026-04-26 | 2026-05-16 | 20 | 1440 | 82.5 | 5.7% | 0.0% | 8 | 1 | 8h | 1 | 0 | 3 | Reallocate partial capacity (~2.7% increase needed) to cover 8 gap-days. Focus on 'l01 → t01' transition (8 days lost, 1 occurrences).
19 | Nc Milling Center (m02) | LOW | 2026-04-13 | 2026-06-12 | 60 | 1920 | 437 | 22.8% | 0.0% | 0 | 0 | 8h | 0 | 0 | 2
20 | Engraving (l03) | LOW | 2026-04-13 | 2026-06-12 | 60 | 1920 | 109.2 | 5.7% | 0.0% | 0 | 0 | 8h | 0 | 0 | 2
21 | Laser Rust Removal (y01) | LOW | 2026-04-13 | 2026-04-26 | 13 | 960 | 110.5 | 11.5% | 0.0% | 4 | 1 | 8h | 1 | 0 | 1 | Reallocate partial capacity (~2.0% increase needed) to cover 4 gap-days. Focus on 'm05 → y01' transition (4 days lost, 1 occurrences).

## Gap Summary
Workflow Gap Analysis — By Workcenter
Total Gaps: | 433 | Total Gap Days: | 3349 | Avg Duration: | 7.7 days
WC Code | WC Name | Total Gap Days | Gap Count | Avg Gap Days | Largest Gap Days | Largest Gap Start | Largest Gap End | Largest Gap Container | Priority
m01 | Cnc Milling Center | 1454 | 131 | 11.1 | 21 | 2026-05-23 | 2026-06-13 | eve1500-3-d02 | High
d03 | Manual Grinding Station | 525 | 95 | 5.5 | 20 | 2026-04-22 | 2026-05-12 | sny42 | High
m03 | Cnc Lathe Center | 430 | 51 | 8.4 | 17 | 2026-04-28 | 2026-05-15 | s357 | High
n01 | Electropolishing Center | 159 | 30 | 5.3 | 14 | 2026-05-01 | 2026-05-15 | sny41 | High
p01 | Automated Packing Station | 44 | 6 | 7.3 | 21 | 2026-05-20 | 2026-06-10 | eve1500-3-d02 | Low
w05 | Tig Welding Center | 37 | 4 | 9.2 | 21 | 2026-04-15 | 2026-05-06 | ed182 | Low
b01 | Plate Bending | 29 | 4 | 7.2 | 11 | 2026-05-01 | 2026-05-12 | l104 | Low
w04 | Mag Welding Center | 25 | 5 | 5.0 | 9 | 2026-05-10 | 2026-05-19 | eve1500-3-d02 | Low
s02 | Disc Sawing Center | 11 | 2 | 5.5 | 7 | 2026-04-18 | 2026-04-25 | h413 | Low
b04 | Plate Rolling | 11 | 1 | 11.0 | 11 | 2026-05-01 | 2026-05-12 | l104 | Low
u01 | Heavy Punching Center | 10 | 3 | 3.3 | 4 | 2026-04-20 | 2026-04-24 | h413 | Low
t01 | Trowalizing Center | 8 | 1 | 8.0 | 8 | 2026-05-01 | 2026-05-09 | s357 | Low
pa01 | Assembly | 7 | 2 | 3.5 | 4 | 2026-05-13 | 2026-05-17 | l104 | Low
y01 | Laser Rust Removal | 4 | 1 | 4.0 | 4 | 2026-04-15 | 2026-04-19 | fer01-d02 | Low
m06 | Drilling And Tapping | 4 | 1 | 4.0 | 4 | 2026-05-28 | 2026-06-01 | eve1500-3-d02 | Low

## Container Timeline
Container Deadline & Status Overview
Container | Deadline | Status | Late Days | Start Date | End Date
m147 | 2026-04-16 | On schedule |  | 2026-04-13 | 2026-04-16
l102 | 2026-04-20 | On schedule |  | 2026-04-14 | 2026-04-16
h411 | 2026-04-20 | On schedule |  | 2026-04-17 | 2026-04-17
ed181 | 2026-04-20 | On schedule |  | 2026-04-13 | 2026-04-16
wk32-wk36 | 2026-04-20 | Late by 5 days | 5 | 2026-04-13 | 2026-04-25
k242 | 2026-04-20 | On schedule |  | 2026-04-13 | 2026-04-16
l101 | 2026-04-20 | On schedule |  | 2026-04-13 | 2026-04-17
hyi62 | 2026-04-20 | Late by 5 days | 5 | 2026-04-13 | 2026-04-25
wk21 | 2026-04-20 | Late by 10 days | 10 | 2026-04-13 | 2026-04-30
h408 | 2026-04-21 | Late by 8 days | 8 | 2026-04-13 | 2026-04-29
sny38 | 2026-04-22 | Late by 4 days | 4 | 2026-04-13 | 2026-04-26
s356 | 2026-04-27 | On schedule |  | 2026-04-19 | 2026-04-26
eve1500-3 | 2026-04-29 | Late by 22 days | 22 | 2026-04-13 | 2026-05-21
sny39 | 2026-04-29 | Late by 15 days | 15 | 2026-04-13 | 2026-05-14
cl169 | 2026-04-29 | Late by 4 days | 4 | 2026-04-22 | 2026-05-03
ke79 | 2026-04-30 | Late by 10 days | 10 | 2026-04-20 | 2026-05-10
eve-1500-2 | 2026-04-30 | On schedule |  | 2026-04-14 | 2026-04-16
fer01 | 2026-04-30 | Late by 3 days | 3 | 2026-04-13 | 2026-05-03
hyi64 | 2026-05-02 | Late by 18 days | 18 | 2026-04-16 | 2026-05-20
h413 | 2026-05-06 | Late by 16 days | 16 | 2026-04-13 | 2026-05-22
sny40 | 2026-05-06 | Late by 9 days | 9 | 2026-04-14 | 2026-05-15
ed182 | 2026-05-06 | Late by 16 days | 16 | 2026-04-13 | 2026-05-22
l103 | 2026-05-15 | Late by 10 days | 10 | 2026-04-30 | 2026-05-25
s357 | 2026-05-15 | Late by 9 days | 9 | 2026-04-16 | 2026-05-24
sny41 | 2026-05-15 | Late by 9 days | 9 | 2026-04-13 | 2026-05-24
m149 | 2026-05-18 | Late by 6 days | 6 | 2026-05-06 | 2026-05-24
l104 | 2026-05-20 | Late by 12 days | 12 | 2026-04-26 | 2026-06-01
sny42 | 2026-05-20 | Late by 5 days | 5 | 2026-04-13 | 2026-05-25
sny43 | 2026-05-27 | Late by 17 days | 17 | 2026-04-13 | 2026-06-13
cl170 | 2026-06-01 | On schedule |  | 2026-05-20 | 2026-05-29
m150 | 2026-06-03 | Late by 14 days | 14 | 2026-05-09 | 2026-06-17
eve1500-3-d02 | 2026-05-21 | Late by 24 days | 24 | 2026-04-14 | 2026-06-14
eve1500-3-d03 | 2026-06-11 | Late by 18 days | 18 | 2026-04-14 | 2026-06-29
eve1500-3-d04 | 2026-07-02 | Late by 7 days | 7 | 2026-04-14 | 2026-07-09
eve-1500-2-d02 | 2026-05-21 | On schedule |  | 2026-04-14 | 2026-04-16
eve-1500-2-d03 | 2026-06-11 | On schedule |  | 2026-04-14 | 2026-04-16
eve-1500-2-d04 | 2026-07-02 | On schedule |  | 2026-04-14 | 2026-04-16
fer01-d02 | 2026-05-08 | Late by 1 days | 1 | 2026-04-13 | 2026-05-09
fer01-d03 | 2026-05-29 | On schedule |  | 2026-04-14 | 2026-05-26

## Employee Statistics
Employee Utilization Statistics
Employee ID | Name | Is Sim | First Day | Last Day | Active Days | Idle Days | Capacity Min | Used Min | Remaining Min | Utilization % | Avg Daily Min | Workcenters
330 | Tang Jixiao | No | 2026-04-13 | 2026-06-14 | 53 | 0 | 21600 | 47761.1 | -26161.1 | 221.1% | 901.2 | Laser Cutting (l01)
397 | Guo Guangsheng | No | 2026-04-13 | 2026-07-09 | 84 | 0 | 30720 | 39235.8 | -8515.8 | 127.7% | 467.1 | Cnc Lathe Center (m03), Cnc Milling Center (m01)
325 | Gavin Liu | No | 2026-04-13 | 2026-07-09 | 83 | 0 | 30720 | 36264 | -5544 | 118.0% | 436.9 | Cnc Milling Center (m01), Cnc Lathe Center (m03), Nc Milling Center (m02), Wire Cutting (c01)
337 | Mei Shijun | No | 2026-04-13 | 2026-07-09 | 79 | 0 | 30720 | 35948.5 | -5228.5 | 117.0% | 455 | Cnc Milling Center (m01), Drilling (m05), Cnc Lathe Center (m03), Nc Milling Center (m02)
341 | Zhao Baojun | No | 2026-04-13 | 2026-07-09 | 75 | 0 | 30720 | 30258.4 | 461.6 | 98.5% | 403.4 | Cnc Milling Center (m01)
340 | Gong Qingguo | No | 2026-04-13 | 2026-06-15 | 59 | 0 | 22080 | 26562.5 | -4482.5 | 120.3% | 450.2 | Manual Grinding Station (d03), Trowalizing Center (t01)
398 | Ma Jishan | No | 2026-04-13 | 2026-06-15 | 56 | 0 | 22080 | 25725.7 | -3645.7 | 116.5% | 459.4 | Mag Welding Center (w04), Tig Welding Center (w05)
373 | Diao Xiaowei | No | 2026-04-13 | 2026-06-15 | 60 | 0 | 22080 | 24119.1 | -2039.1 | 109.2% | 402 | Assembly (pa01), Automated Packing Station (p01), Helper Work General (d05), Checking (q02)
336 | Yu Wei | No | 2026-04-13 | 2026-06-14 | 56 | 0 | 21600 | 23693.6 | -2093.6 | 109.7% | 423.1 | Band Sawing (s01), Drilling And Tapping (m06), Cnc Lathe Center (m03), Drilling (m05)
360 | Shang Hechang | No | 2026-04-13 | 2026-06-15 | 54 | 0 | 22080 | 23334 | -1254 | 105.7% | 432.1 | Manual Grinding Station (d03), Helper Work General (d05), Automated Packing Station (p01), Assembly (pa01)
365 | Liu Jiankai | No | 2026-04-13 | 2026-06-15 | 51 | 0 | 22080 | 22778.1 | -698.1 | 103.2% | 446.6 | Mag Welding Center (w04)
366 | Li Zhipeng | No | 2026-04-13 | 2026-06-15 | 48 | 0 | 22080 | 21850 | 230 | 99.0% | 455.2 | Mag Welding Center (w04)
364 | Zhao Wei | No | 2026-04-13 | 2026-06-08 | 48 | 0 | 19680 | 21829.6 | -2149.6 | 110.9% | 454.8 | Tig Welding Center (w05), Mag Welding Center (w04)
379 | Wang Cunxiang | No | 2026-04-13 | 2026-06-15 | 56 | 0 | 22080 | 21768.1 | 311.9 | 98.6% | 388.7 | Assembly (pa01), Drilling And Tapping (m06), Helper Work General (d05), Automated Packing Station (p01)
377 | Yang Xiaoxiang | No | 2026-04-13 | 2026-06-15 | 56 | 0 | 22080 | 21589.2 | 490.8 | 97.8% | 385.5 | Assembly (pa01), Automated Packing Station (p01), Helper Work General (d05)
367 | Chang Zhiju | No | 2026-04-13 | 2026-06-15 | 48 | 0 | 22080 | 21274.7 | 805.3 | 96.4% | 443.2 | Mag Welding Center (w04), Tig Welding Center (w05)
328 | Sun Guofeng | No | 2026-04-13 | 2026-06-08 | 46 | 0 | 19680 | 21270.6 | -1590.6 | 108.1% | 462.4 | Tig Welding Center (w05), Mag Welding Center (w04), Laser Welding (w06)
339 | Zhang Liyuan | No | 2026-04-13 | 2026-06-13 | 45 | 0 | 21600 | 19985.5 | 1614.5 | 92.5% | 444.1 | Manual Grinding Station (d03), Helper Work General (d05)
376 | Li Lefeng | No | 2026-04-13 | 2026-06-14 | 46 | 0 | 21600 | 19215.9 | 2384.1 | 89.0% | 417.7 | Assembly (pa01), Automated Packing Station (p01), Helper Work General (d05), Electropolishing Center (n01)
351 | Yin Yanqiu | No | 2026-04-13 | 2026-06-08 | 43 | 0 | 19680 | 18986.8 | 693.2 | 96.5% | 441.6 | Tig Welding Center (w05), Mag Welding Center (w04)
355 | JI Yipin | No | 2026-04-13 | 2026-06-03 | 40 | 0 | 18240 | 18920.4 | -680.4 | 103.7% | 473 | Tig Welding Center (w05), Manual Grinding Station (d03), Trowalizing Center (t01), Mag Welding Center (w04)
338 | Luo Jun | No | 2026-04-13 | 2026-06-08 | 45 | 0 | 19680 | 18562.2 | 1117.8 | 94.3% | 412.5 | Trowalizing Center (t01), Manual Grinding Station (d03), Assembly (pa01)
345 | Chen Yuwen | No | 2026-04-13 | 2026-06-15 | 40 | 6 | 22080 | 18502.8 | 3577.2 | 83.8% | 462.6 | Laser Welding (w06), Tig Welding Center (w05), Mag Welding Center (w04), Stud Welding (w03)
344 | Zhang Chongliang | No | 2026-04-13 | 2026-06-15 | 40 | 6 | 22080 | 18223.5 | 3856.5 | 82.5% | 455.6 | Tig Welding Center (w05), Mag Welding Center (w04), Laser Welding (w06), Engraving (l03)
372 | Shao Changjun | No | 2026-04-13 | 2026-06-15 | 40 | 6 | 22080 | 18117.1 | 3962.9 | 82.1% | 452.9 | Mag Welding Center (w04)
375 | Xu Qinye | No | 2026-04-13 | 2026-06-14 | 47 | 0 | 21600 | 17996.9 | 3603.1 | 83.3% | 382.9 | Assembly (pa01), Electropolishing Center (n01), Helper Work General (d05)
374 | Zhang Weizhao | No | 2026-04-13 | 2026-06-14 | 44 | 1 | 21600 | 17984.6 | 3615.4 | 83.3% | 408.7 | Automated Packing Station (p01), Helper Work General (d05), Riveting Center (r01), Assembly (pa01), Checking (q02)
335 | Jiang Xiugang | No | 2026-04-13 | 2026-06-18 | 55 | 0 | 23520 | 17778.8 | 5741.2 | 75.6% | 323.3 | Drilling (m05), Plate Bending (b01), Nc Milling Center (m02), Cnc Milling Center (m01)
356 | Wang Xuelin | No | 2026-04-13 | 2026-06-03 | 38 | 0 | 18240 | 17638.7 | 601.3 | 96.7% | 464.2 | Tig Welding Center (w05), Mag Welding Center (w04), Laser Welding (w06)
348 | Xia Hongxian | No | 2026-04-13 | 2026-06-15 | 39 | 7 | 22080 | 17491.1 | 4588.9 | 79.2% | 448.5 | Tig Welding Center (w05), Mag Welding Center (w04), Stud Welding (w03), Laser Welding (w06)
347 | Wu Lianjun | No | 2026-04-13 | 2026-06-15 | 42 | 4 | 22080 | 16874.9 | 5205.1 | 76.4% | 401.8 | Plate Rolling (b04), Mag Welding Center (w04), Laser Rust Removal (y01), Tig Welding Center (w05), Laser Welding (w06)
329 | Cai Zhihua | No | 2026-04-13 | 2026-06-14 | 49 | 0 | 21600 | 16859.1 | 4740.9 | 78.1% | 344.1 | Plate Bending (b01), Engraving (l03), Pipe Bending (b02), Pipe Laser (l02)
390 | Huang Hao | No | 2026-04-13 | 2026-06-15 | 37 | 9 | 22080 | 16552.6 | 5527.4 | 75.0% | 447.4 | Mag Welding Center (w04)
380 | Zhang Zhen | No | 2026-04-13 | 2026-06-14 | 42 | 3 | 21600 | 16368.3 | 5231.7 | 75.8% | 389.7 | Assembly (pa01), Helper Work General (d05), Laser Rust Removal (y01), Automated Packing Station (p01)
350 | Yin Xianfa | No | 2026-04-13 | 2026-06-13 | 38 | 7 | 21600 | 16222.8 | 5377.2 | 75.1% | 426.9 | Stud Welding (w03), Mag Welding Center (w04), Tig Welding Center (w05), Laser Welding (w06)
334 | Gao Quanhe | No | 2026-04-13 | 2026-06-15 | 50 | 0 | 22080 | 16111 | 5969 | 73.0% | 322.2 | Drilling (m05), Pipe Bending (b02), Cnc Lathe Center (m03), Nc Milling Center (m02)
346 | Wang Xushun | No | 2026-04-13 | 2026-06-15 | 37 | 9 | 22080 | 16047.7 | 6032.3 | 72.7% | 433.7 | Tig Welding Center (w05), Mag Welding Center (w04)
343 | Wang Xiaochen | No | 2026-04-13 | 2026-06-07 | 39 | 1 | 19200 | 15788.9 | 3411.1 | 82.2% | 404.8 | Cnc Lathe Center (m03)
349 | Wang Ruifei | No | 2026-04-13 | 2026-06-13 | 37 | 8 | 21600 | 15730 | 5870 | 72.8% | 425.1 | Tig Welding Center (w05), Mag Welding Center (w04), Laser Welding (w06)
361 | Jiang Quannian | No | 2026-04-14 | 2026-05-30 | 34 | 0 | 16320 | 15520 | 800 | 95.1% | 456.5 | Manual Grinding Station (d03)
382 | Wang Ye | No | 2026-04-14 | 2026-05-19 | 30 | 0 | 12480 | 14595.9 | -2115.9 | 117.0% | 486.5 | Manual Grinding Station (d03)
333 | Sun Gongxu | No | 2026-04-13 | 2026-06-07 | 42 | 0 | 19200 | 14511.9 | 4688.1 | 75.6% | 345.5 | Band Sawing (s01), Disc Sawing Center (s02), Helper Work General (d05), Heavy Punching Center (u01)
352 | Ji Zhongwei | No | 2026-04-13 | 2026-06-08 | 33 | 8 | 19680 | 14473.6 | 5206.4 | 73.5% | 438.6 | Tig Welding Center (w05), Mag Welding Center (w04)
354 | Song Zhilong | No | 2026-04-14 | 2026-06-08 | 32 | 8 | 19200 | 13750.4 | 5449.6 | 71.6% | 429.7 | Mag Welding Center (w04), Tig Welding Center (w05), Stud Welding (w03)
363 | Wang Yongxi | No | 2026-04-14 | 2026-06-08 | 30 | 10 | 19200 | 13563.1 | 5636.9 | 70.6% | 452.1 | Mag Welding Center (w04), Tig Welding Center (w05)
353 | Gong Qingsuo | No | 2026-04-14 | 2026-06-08 | 30 | 10 | 19200 | 13245.3 | 5954.7 | 69.0% | 441.5 | Mag Welding Center (w04), Tig Welding Center (w05)
357 | Sui Sixian | No | 2026-04-14 | 2026-05-26 | 28 | 3 | 14880 | 12790 | 2090 | 86.0% | 456.8 | Mag Welding Center (w04), Laser Welding (w06)
358 | Cao Cheng | No | 2026-04-14 | 2026-05-26 | 30 | 1 | 14880 | 12668.3 | 2211.7 | 85.1% | 422.3 | Mag Welding Center (w04), Tig Welding Center (w05)
362 | Zhang Baohua | No | 2026-04-13 | 2026-05-25 | 27 | 4 | 14880 | 11223.8 | 3656.2 | 75.4% | 415.7 | Wire Cutting (c01), Assembly (pa01), Automated Packing Station (p01), Plate Rolling (b04)
378 | Liu Xu | No | 2026-04-15 | 2026-06-14 | 33 | 10 | 20640 | 10846.4 | 9793.6 | 52.6% | 328.7 | Helper Work General (d05), Assembly (pa01), Electropolishing Center (n01)
331 | Huang Zelun | No | 2026-04-13 | 2026-06-09 | 31 | 11 | 20160 | 9933.5 | 10226.5 | 49.3% | 320.4 | Pipe Laser (l02), Plate Bending (b01), Pipe Bending (b02), Plate Rolling (b04)
332 | Sun Kewen | No | 2026-04-13 | 2026-06-06 | 33 | 7 | 19200 | 9661 | 9539 | 50.3% | 292.8 | Heavy Punching Center (u01), Pipe Bending (b02), Band Sawing (s01), Plate Bending (b01), Pipe Laser (l02)
342 | Bing Zhaochun | No | 2026-04-14 | 2026-06-05 | 25 | 14 | 18720 | 8035.8 | 10684.2 | 42.9% | 321.4 | Plate Bending (b01)
383 | Zhao Ruifei | No | 2026-04-13 | 2026-05-30 | 15 | 20 | 16800 | 3043.2 | 13756.8 | 18.1% | 202.9 | Drilling And Tapping (m06)
359 | Wang Jian | No | 2026-04-15 | 2026-06-07 | 17 | 21 | 18240 | 2359.7 | 15880.3 | 12.9% | 138.8 | Pipe Bending (b02), Plate Bending (b01), Pipe Laser (l02), Plate Rolling (b04), Laser Cutting (l01)
QC_TEAM | Quality Control | No | 2026-04-23 | 2026-04-23 | 1 | 0 | 480 | 30 | 450 | 6.2% | 30 | Quality Testing Center (q01)